## How to use
First US and EU launch: pharmacovigilance readiness checklist (SciEngage, October 2026)
What this is: the safety tasks a small biotech should close before and just after a first marketing authorisation.
How to use it: choose a status in the blue column for each task. The summary counts what is done, in progress or not started by phase.
Owner column: replace the suggested owners with named people. Every task needs one accountable name, even when a partner does the work.
This is not legal advice. Confirm timelines with your regulatory lead against the current regulations listed in the Reference column.
Read the full guide: https://sciengage.co/blog/pharmacovigilance-partner-first-us-eu-launch

## Checklist
Phase | Area | Task | Suggested owner | Reference | Status | Named owner | Target date | Notes
12-18 months before filing | Safety database | Select and validate the safety database; confirm E2B(R3) output | Sponsor / PV partner | FDA ESG NextGen E2B(R3) from 1 Oct 2026 (91 FR 17284) | Not started
12-18 months before filing | Intake map | List every channel that could receive an adverse event and name its owner | Sponsor | 21 CFR 314.80 and 600.80; GVP Module VI | Not started
12-18 months before filing | QPPV | Appoint EU QPPV and deputy; decide UK QPPV or UK national contact | Sponsor / PV partner | Directive 2001/83/EC Art. 104; MHRA guidance updated 30 Sep 2026 | Not started
12-18 months before filing | Trial-to-market hand-off | Agree how trial safety data, DSURs and the reference safety information move to the post-market team | Sponsor / CRO / PV partner | ICH E2F; GVP Module VII | Not started
At filing | EU risk management plan | Submit the RMP with the marketing authorisation application | Regulatory lead | EMA RMP guidance; Implementing Regulation (EU) 520/2012 | Not started
At filing | PSMF | Draft the pharmacovigilance system master file and its location | QPPV / PV partner | Implementing Regulation (EU) 520/2012 | Not started
At filing | US REMS | Confirm with FDA early whether a REMS is needed | Regulatory lead | FDCA 505-1; FDA REMS guidance | Not started
Review to approval | Safety data exchange agreements | Sign SDEAs with every licensee, distributor and service provider, including clock-start definitions | Sponsor / Legal | GVP Module VI; MAH retains responsibility when outsourcing | Not started
Review to approval | Mock inspection | Run a mock inspection across intake, case processing, signals and the PSMF | QA / PV partner | GVP Module III; FDA PV inspection programme | Not started
Review to approval | Literature and medical information | Set up literature screening beyond EMA's monitored list and a medical information line | PV partner | EMA Medical Literature Monitoring; GVP Module VI | Not started
First 12 months on market | Expedited reporting | Track 15-day reports for serious unexpected US cases and serious EU cases | PV partner | 21 CFR 314.80; Directive 2001/83/EC Art. 107 | Not started
First 12 months on market | US periodic reports | Submit quarterly for three years, then annually (PBRER may replace PADER with agreement) | PV partner / Regulatory | 21 CFR 314.80(c)(2); FDA PBRER guidance | Not started
First 12 months on market | EU PSURs | Follow EURD list dates and submit PSURs through the PSUR repository | QPPV / PV partner | EURD list; Directive 2001/83/EC Art. 107c | Not started
First 12 months on market | Signal management | Run documented signal reviews with recorded decisions and timelines | QPPV / Safety physician | GVP Module IX; EudraVigilance signal monitoring | Not started

## Summary
Phase | Tasks | Done | In progress | Not started | Percent done
12-18 months before filing
At filing
Review to approval
First 12 months on market